## Start here
127 · BUILD TRACK · BUILDER
Launch Countdown (filled example)
Every step from picking a launch date to the week after launch, with a do-by date for each so nothing important gets missed.
This copy is filled in with a made-up example so you can see what good looks like. Use the blank file for your own business.
HOW TO USE IT
1. Open the Setup tab and type your launch date. Pick a day about 14 days out.
2. Every task in the Countdown tab gets its do-by date from that one cell.
3. Mark each task To do, Doing or Done. Overdue tasks turn red, tasks due in two days turn yellow.
4. The Setup tab shows your progress and the next task due.
5. Launch week: do the day's tasks, log every reply in the Pipeline Tracker and every objection in the Objection Log.
CELL COLORS
White cells: you type here.
Grey cells: calculated for you. Leave them alone.
Lilac cells: the answer you came for.
OPEN IT ANYWHERE
Google Sheets: go to sheets.new, then File > Import > Upload this file > Replace spreadsheet. Formulas and dropdowns come with it.
Excel: double-click the file. Numbers on a Mac: open it with Numbers.
Phone: upload it to Google Drive, then open it in the Google Sheets app.
Registration, taxes and business money rules depend on where you live. This is not legal or tax advice. Check your local rules or ask a professional.
Make today day one. · 127group.io
Template drafted from Eli Christiansen's frameworks. © 127 Group LLC. For your own business use.

## Setup
Launch Countdown
Type your launch date. Everything else fills in.
YOUR LAUNCH
Launch day
Days until launch
The three people checking in on you | Mom, Coach Rivera, Dev
PROGRESS
Tasks
Done
Percent done
Overdue
Next task due
Its do-by date
Note on A5: About 14 days from today.

## Countdown
Launch Countdown
Do-by dates come from your launch date on the Setup tab.
# | Phase | Task | Days from launch | Do by | Days left | Status | Done on | Notes | id | open
1 | Today | Pick a launch date about 14 days out and put it on your calendar. | -14 |  |  | Done |  |  | launch-countdown.today.1
2 | Today | Text three people the date and ask them to check in on you. | -14 |  |  | Done |  |  | launch-countdown.today.2
3 | Today | Copy this countdown into Google Sheets, Notion or your notes app. | -14 |  |  | Done |  |  | launch-countdown.today.3
4 | Two weeks before: set up the foundation | Finish your One-Page Offer. | -8 |  |  | Done |  |  | launch-countdown.t14.1
5 | Two weeks before: set up the foundation | Fill in your Landing Page Brief and build the page. | -8 |  |  | Done |  |  | launch-countdown.t14.2
6 | Two weeks before: set up the foundation | Run the five-point pre-launch check on your phone. | -8 |  |  | Done |  |  | launch-countdown.t14.3
7 | Two weeks before: set up the foundation | Set up payments: Shopify Payments for a store, or a payment link for a service. | -8 |  |  | Done |  |  | launch-countdown.t14.4
8 | Two weeks before: set up the foundation | Make a real payment with your own card, then refund it. | -8 |  |  | Done |  |  | launch-countdown.t14.5
9 | Two weeks before: set up the foundation | Look into registering your business. Check your local rules or ask a professional. This isn't legal or tax advice. | -8 |  |  | Done |  |  | launch-countdown.t14.6
10 | Two weeks before: set up the foundation | Set up a separate way to track business money. See Before You Take Money. | -8 |  |  | Done |  |  | launch-countdown.t14.7
11 | Two weeks before: set up the foundation | Write your delivery steps: everything that happens after someone pays. | -8 |  |  | Done |  |  | launch-countdown.t14.8
12 | Two weeks before: set up the foundation | Do one full test delivery with a friend. | -8 |  |  | Done |  |  | launch-countdown.t14.9
13 | One week before: warm up your list | Write your warm list in the Pipeline Tracker. Aim for 30 names. | -1 |  |  | To do |  |  | launch-countdown.t7.1
14 | One week before: warm up your list | Mark the 10 people most likely to buy. | -1 |  |  | Doing |  |  | launch-countdown.t7.2
15 | One week before: warm up your list | Send those 10 a personal heads-up and ask if you can send them the link first. | -1 |  |  | To do |  |  | launch-countdown.t7.3
16 | One week before: warm up your list | Post once about what you're building and why. | -1 |  |  | Doing |  |  | launch-countdown.t7.4
17 | One week before: warm up your list | Draft your launch post, your launch DM and your launch story. | -1 |  |  | To do |  |  | launch-countdown.t7.5
18 | One week before: warm up your list | Write the welcome message every new customer gets. | -1 |  |  | Doing |  |  | launch-countdown.t7.6
19 | One week before: warm up your list | Write your three feedback questions. | -1 |  |  | To do |  |  | launch-countdown.t7.7
20 | One week before: warm up your list | Open the Objection Log so you can capture every "but" during launch week. | -1 |  |  | Doing |  |  | launch-countdown.t7.8
21 | Launch day | Send personal DMs to your top 10. One at a time, never a group message. | 0 | [5 empty] | launch-countdown.d1.1
22 | Launch day | Post your launch post and your story. | 0 | [5 empty] | launch-countdown.d1.2
23 | Launch day | Reply to every comment and DM the same day. | 0 | [5 empty] | launch-countdown.d1.3
24 | Launch day | Log every reply and sale in the Pipeline Tracker. | 0 | [5 empty] | launch-countdown.d1.4
25 | Day 2 | Message the next 20 people on your warm list. | 1 | [5 empty] | launch-countdown.d2.1
26 | Day 2 | Ask your day 1 buyers if they know one person who'd want this. | 1 | [5 empty] | launch-countdown.d2.2
27 | Day 3 | Post something useful about the problem you solve, like a before and after or a quick tip. | 2 | [5 empty] | launch-countdown.d3.1
28 | Day 3 | Log every objection you've heard so far in the Objection Log. | 2 | [5 empty] | launch-countdown.d3.2
29 | Day 4 | Send one short, friendly follow-up to every maybe and every no-reply. | 3 | [5 empty] | launch-countdown.d4.1
30 | Day 5 | Deliver to your first customers with extra care. Over-deliver on the first orders. | 4 | [5 empty] | launch-countdown.d5.1
31 | Day 6 | Post a real update: what happened and what you learned. | 5 | [5 empty] | launch-countdown.d6.1
32 | Day 6 | Share a customer result only with their permission. | 5 | [5 empty] | launch-countdown.d6.2
33 | Day 7 | Count messages sent, replies, sales and objections. | 6 | [5 empty] | launch-countdown.d7.1
34 | Day 7 | Write down the one thing you'll change next week. | 6 | [5 empty] | launch-countdown.d7.2
35 | The week after: ask, learn, decide | Thank every customer within three days of delivery. | 13 | [5 empty] | launch-countdown.after.1
36 | The week after: ask, learn, decide | Ask every customer: What almost stopped you from buying? What was the best part? What would you change? | 13 | [5 empty] | launch-countdown.after.2
37 | The week after: ask, learn, decide | Ask happy customers if you can share their words or a photo. Use only what they approve. | 13 | [5 empty] | launch-countdown.after.3
38 | The week after: ask, learn, decide | Ask every non-buyer: What would have made it a yes? | 13 | [5 empty] | launch-countdown.after.4
39 | The week after: ask, learn, decide | Update your FAQ and landing page from the Objection Log. | 13 | [5 empty] | launch-countdown.after.5
40 | The week after: ask, learn, decide | Find the message, post or person that drove the most sales, and ask why it worked. | 13 | [5 empty] | launch-countdown.after.6
41 | The week after: ask, learn, decide | Pick one thing to do more of next week. | 13 | [5 empty] | launch-countdown.after.7
42 | The week after: ask, learn, decide | Set up simple revenue and expense tracking, and ask a professional about taxes where you live. | 13 | [5 empty] | launch-countdown.after.8
Formulas:
Days left = IF(OR([Do by]="",[Status]="Done"),"",[Do by]-TODAY())